## Fixes
# | Issue Found By | In Module/Class | Tested with (Software/Modules) | Description (Before Fix) |  |  | Issue Severity | Fixed by | Fix Notes
|  |  |  | Action | Expected Result | Actual Result
1 | Minor Errors
1.1 | Josh | Card.java | TestNG CardTest.java TestFactory.java | Check if card.equals(card.clone()) | True | False [.equals() not currently implemented in Card.java, will only .equals() itself.] | Minor | Josh | added hashCode() and equals() functions to Card.class.
1.2 | Josh | CardStack.java | TestNG CardStackTest.java TestFactory.java | .getAvailableCards() | Child class overrides parent function when needed. | Parent calls "instanceof Column" | Minor | Josh
|  |  |  | Open and interact with Stats panel. | Panel should not be alterable | User can alter JTextArea | Minor | Jesse | change JTextArea.setEditable to false
1.3 | Jesse | UI | Manual | Completed the Game | Fireworks panel should display, and on top of game panel | Fireworks panel loads behind Solitaire Panel | Minor | Jesse | change JOptionPane to JDialog and move addMouseListener to work with the latter.
| Jesse | UI | Manual | Completed the Game w/ Animation off | Music should play, Stop Music panel should display on top of game panel | Stop Music panel displays at (0,0). Text is off-center | Minor |  | change position of Stop Music panel relative to game panel; center text
1.4 | Lizz | Card.java | FindBugs | card class has bug with clone method (could be damaging in other circumstances) | Clone of Card | Clone of Card | Minor | Lizz | implements cloneable to class
1.5 | Lizz | WinScreen.java | FindBugs | sound.run (could be damaging in other circumstances) | Plays music | Plays music | Minor | Lizz | change .run() to .start() because threads are supposed to use start methods
1.6 | Lizz | SoundThread.java | FingBugs | Public void run() (could be damaging in other circumstances) | Begins sound thread | Begins sound thread | Minor | Lizz | change run() to start() because threads are supposed to use start methods
2 | Moderate Errors
2.1 | Josh | CardStack.java | TestNG CardStackTest.java TestFactory.java | getStack(int) | gets a stack of (int) cards from the bottom. | ArrayIndexOutOfBoundsException: -1 | Moderate | Kailab
2.2 | Josh | UI | Manual | Slight mouse move between mouse_down and mouse_up (still on same graphical object). | Swing object reacts if clicked. | Swing object does not react. | Moderate | Josh | MouseRelease now triggers click.
3 | Serious Issues
3.1 | Kailab | UI | Manual | Undo Stack move using Ctrl-Z | Stack Moves back to Last Position. | Fail, Stack does not Move. | Serious | Kailab
3.2 | Kailab | UI | Manual | Move Cards to Valid Positions | Cards move to Designated Position. | Fail | Serious | Kailab
3.3 | Kailab | UI | Manual | Move Cards to Valid Positions(Added Fix) | Cards move to Designated Position. | Fail for only moving to Columns | Serious | Kailab
4 | Documentation [javaDocs and additional comments].
4.1 | Lizz | AcePile.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.2 | Lizz | DiscardPileTest.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.3 | Lizz | ColumnTest.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.4 | Lizz | SingleCellTest.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.5 | Lizz | CardTest.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.6 | Lizz | AcePileTest.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
4.7 | Lizz | CardStack.java | Manual/ Eclipse | Add java doc | Easy to understand comments on what method and classes are doing what | Easy to understand comments on what method and classes are doing what | Minor | Lizz
5 | Enhancements [Add to list once you plan on or start working on an enhacement].
5.1 | Josh | pom.xml | Manual | Build Project | Build Path Included as part of the Project | Basic java project does not include Build Paths. | Minor | Josh | Maven support (optional) adds build paths to the project.
5.2 | Lizz | DealDeck.java | Manual | Makes the hard difficulty hard instead of impossible | Difficulty hard is no longer impossible | I was able to beat it once | Moderate | Lizz | Increased the number of cycles through a deck on hard difficulty
5.3 | Lizz | ChangeOptions.java DealDeck.java | Manual | Another difficulty impossible | So hard im pretty sure no one will be able to beat it | Could not beat it | Minor | Lizz | Gave the user one to two cycles depending on the amount of cards they put in the discard pile
5.4 | Lizz | FourRowSolitaire.java | Manual | Stats now include new difficulty | Display impossible difficuly stats | Display impossible difficuly stats | Minor | Lizz | Did not have the option now the game does
5.5 | Josh | Card.java (+Related classes) | Manual | Card.java fields. | Suit, Number (Ace-King), and Color as enumerations. | Fields were stored as Strings and integers, with public states. | Minor /Complex | Josh | New public enums with related functions: Card.Suit, Card.Number, and Card.Color
6 | Not added.
6.1 |  | Misc | * | Test Coverage | 95%+ | Varies | Minor | Some updates broke prior coverage tests, not enough time remains to rebuild all test cases. Primary tests (focusing on units, some intergration, and manual/System testing) still successful.
6.2 |  | * | N/A | Documentation / javaDoc | Full | Limited | Minor | Full doucmentation would take an extended timeframe, majority of time available was spent on bug fixes and improvements.
6.2 |  | * | N/A | Rebuild for better coding and MVC (Model / View / Controller) classes. | Not-Expected | Minor (Card.java improved). | Minor | Part of potential plan, again time issues prevented a full rewrite. Some improvements done, also shows ideas towards further structual changes (see Card.java's enums).
Note on D1: jUnit TestNG Jubula Manual (etc)
Note on H1: OK: Works as-is. Minor: Won't effect opperations. Moderate: May provide minor difficulty, game still completable. Serious: Makes game unplayable or near-unplayable. Critical: Breaks computer operations (crash, file del, etc).

## Perform Test Plan
# | Ran By | Module/Class | Tested with (Software/Modules) | Description |  |  | Issue Severity | Additional Notes | Fixed by | Fix Notes
|  |  |  | Action | Expected Result | Actual Result
1 | Unit Testing [Classes that work primaraily on their own]
1.1 | Josh | Card.java | TestNG CardTest.java TestFactory.java
1.1.1 |  |  |  | getNumber(), getSuite(), getFullNumber() | Returns same values as entered. | Pass | OK
1.1.2 |  |  |  | getColor() | 0=Black, 1=Red | Pass | OK
1.1.3 |  |  |  | Check if card.equals(card.clone()) | True | False | Minor | [.equals() not currently implemented in Card.java, will only .equals() itself.]
1.2 1.2.1-1.2.3 | Lizz |  | Junit- AcePileTest.java | getSuit(), push(), isValidMove_Card() | suit, card, true | pass, pass, pass | ok
1.3 1.3.1-1.3.6 | Lizz |  | Junit- CardTest.java | highlight(), unhighlight(), isFaceUp(), isFaceDown(), isValidSuit(), getImage() | true, false, true, false, true, cardimagestring | pass, pass, pass, pass, pass, pass | ok
1.4 1.4.1-1.4.2 | Lizz |  | Junit- ColumnTest.java | push(), isValidMove_Card() |  | pass, pass | ok
1.5 1.5.1-1.5.2 | Lizz |  | Junit- SingleCellTest.java | push(), isValidMove_Card() |  | pass, pass | ok
1.6 1.6.1-1.6.6 | Lizz |  | Junit- DiscardPileTest.java | setView(), push_Card(), addCard(), isValidMove_Card(), setDrawCount(), getNumViewable() |  | pass, pass, pass, pass, pass, pass | ok
2 | Integration Testing [Classes primaraily based on other classes]
2.1 | Josh | CardStack.java | TestNG CardStackTest.java TestFactory.java | Create entire deck (52 Cards) and stacks to test.
2.1.1 |  |  |  | .add(), .push(), .peek(), .pop() | Card will be properly pushed, peeked, and poked in order. | Pass | OK
2.1.2 |  |  |  | .addStack(stack), pop(stack), .getStack(card), | Add, check, and remove a sub-stack. | Pass | OK | Stacks are added in reverse order.
2.1.3 |  |  |  | .getAvailableCards() | Stack of available cards. | Pass | OK/Minor* | *Function checks for "instanceof Column", should be overridden by child class instead. It works as-is, but should be fixed.
2.1.4 |  |  |  | .length(), .isEmpty() | Size of stack | Pass | OK
2.1.5 |  |  |  | getStack(int) | gets a stack of (int) cards from the bottom. | ArrayIndexOutOfBoundsException: -1 | Moderate
2.1.6 |  |  |  | .getBottom(), .getCardAtLocation(), .search() | Get card(s) at various points. | Pass | OK
2.2 | Josh | Deck.java | TestNG DeckTest.java TestFactory.java | On Creation, deck should generate with shuffled 52 card set.
2.2.1 |  |  |  | .getDeck() | Shuffled 52 card set. | Pass | OK
2.2.2 |  |  |  | .getDeck(LinkedList<Integer>) | Shuffled sub card set. | Pass | OK
2.2.3 |  |  |  | .shuffle() | Reshuffle deck. | Pass | OK
2.3 | Josh | DealDeck.java | TestNG DealDeckTest.java TestFactory.java | On Creation, linked with Discard Pile
2.3.1 |  |  |  | .setDifficulty() | Sets difficulty value | Sets Through Limit | Moderate | difficulty var not used by class.
2.3.2 |  |  |  | .setDrawCount() | sets deckThroughLimit | Pass | OK
2.3.3 |  |  |  | .setDeckThroughs(), .getDeckThroughs() | get/set numTimesThroughDeck | Pass | OK
2.3.4 |  |  |  | .hasDealsLeft() | ?(numTimesThroughDeck >= deckThroughLimit) | Pass* | OK/Minor* | Stored as seperate variable, should check each time called.
2.3.5 |  |  |  | Cards popped from DealDeck | automatically added to linked discardPile | Pass | OK
2.4 | Josh | SolitaireBoard.java | Manual | On Creation, should have proper amounts and values for all stacks. |  |  |  | Column[4] columns DiscardPile discardPile DealDeck dealDeck AcePile[4] acePiles SingleCell[4] cellsAll fields should have the correct values on start. All further interactions tested within System and UI Testing.
2.4.1 |  |  |  | acePiles[4], discardPile | Empty | Check | OK
2.4.2 |  |  |  | cells[4] | Single Card | Check | OK
2.4.3 |  |  |  | columns[4] | 5 Random Cards | Check | OK
2.4.4 |  |  |  | dealDeck | Remaining Cards, at random. | Check | OK
3 | System Testing
3.1a | General
3.1.1 | Josh | UI | Manual | Slight mouse move between mouse_down and mouse_up (still on same graphical object). | Swing object reacts if clicked. | Swing object does not react. | Serious
3.1.2 | Jesse | UI | Manual | Completed the Game | Fireworks effects | Fireworks panel loads behind Solitaire Panel |  | Fireworks panel should load on top of game panel
3.1.3 | Jesse | UI | Manual | Completed the Game | Music plays | Pass
3.2 | Menu Options
3.2.1 | Jesse | UI | Jubula | Start New Game: Select New Game menu bar item | A new Solitaire board is instantiated | Pass
3.2.2 |  |  |  | Start New Game: Press F2 key | A new Solitaire board is instantiated | Pass
3.2.3 |  |  |  | Undo Last Move: Select Undo menu bar item | Player's last move is reversed | Pass
3.2.4 |  |  |  | Undo Last Move: Press Ctrl+Z | Player's last move is reversed | Pass
3.2.5 |  |  |  | Receive Hint: Select Hint menu bar item | Hint dialogue is instantiated | Pass
3.2.6 |  |  |  | Receive Hint: Press H key | Hint dialogue is instantiated | Pass
3.2.7 |  |  |  | Close Hint: Click OK button | Hint dialogue is closed | Pass
3.2.8 |  |  |  | Close Hint: Press Enter key | Hint dialogue is closed | Pass
3.2.9 |  |  |  | View Stats: Select Statistics menu bar item | Stats dialogue is instantiated | Pass
3.2.10 |  |  |  | View Stats: Press F4 key | Stats dialogue is instantiated | Pass
3.2.11 |  |  |  | Close Stats: Click Close button | Stats dialogue is closed | Pass
3.2.12 |  |  |  | Close Stats: Press Enter key | Stats dialogue is closed | Pass
3.2.13 |  |  |  | Reset Stats: Click Reset button | All stat values set to zero / Stats dialogue is closed | Pass
3.2.14 |  |  |  | Open Change Appearance: Select Change Appearance menu bar item | Change Appearance dialogue is instantiated | Pass
3.2.15 |  |  |  | Open Change Appearance: Press F7 key | Change Appearance dialogue is instantiated | Pass
3.2.16 |  |  |  | Confirm Change Appearance: Click Choose This Setup button | Appearance settings are saved | Pass
3.2.17 |  |  |  | Change Appearance: Select Background 1 | Background changes to Background 1 on confirmation | Pass
3.2.18 |  |  |  | Change Appearance: Select Background 2 | Background changes to Background 2 on confirmation | Pass
3.2.19 |  |  |  | Change Appearance: Select Background 3 | Background changes to Background 3 on confirmation | Pass
3.2.20 |  |  |  | Change Appearance: Select Deck 1 | Deck back changes to Deck 1 on New Game | Pass
3.2.21 |  |  |  | Change Appearance: Select Deck 2 | Deck back changes to Deck 1 on New Game | Pass
3.2.22 |  |  |  | Change Appearance: Select Deck 3 | Deck back changes to Deck 1 on New Game | Pass
3.2.23 |  |  |  | Exit Program: Select Exit menu bar item | Program execution ends/ Window is closed | Pass
3.2.24 |  |  |  | View Help: Select View Help menu bar item | View Help dialogue is opened | Pass
3.2.25 |  |  |  | View Help: Press F1 key | View Help dialogue is opened | Pass
3.2.26 |  |  |  | Close Help: Click OK button | View Help dialogue is closed | Pass
3.2.27 |  |  |  | Close Help: Press Enter key | View Help dialogue is closed | Pass
3.2.28 |  |  |  | View About Game: Select About Game menu bar item | About Game dialogue is opened | Pass
3.2.29 |  |  |  | Close About Game: Click OK button | About Game dialogue is closed | Pass
3.2.30 |  |  |  | Close About Game: Press Enter key | About Game dialogue is closed | Pass
3.2.31 |  |  |  | Check for Update: Select Check for Update menu bar item | User is redirected to the project's Source Forge page: https://sourceforge.net/projects/fourrow/ | Pass
3.2.32 |  |  |  | Options: Select Options menu bar item | Options dialogue is opened | Pass
3.2.33 |  |  |  | Options: Press F5 key | Options dialogue is opened | Pass
3.2.34 | Jesse | UI | Manual | Options: Select 1 Card Draw | Cards are drawn 1 at a time | Pass
3.2.35 |  |  |  | Options: Select 3 Card Draw | Cards are drawn 3 at a time | Pass
3.2.36 |  |  |  | Options: Set Difficulty: Easy | Flip throughs set, dependent on draws: 1 Draw: 3 flip throughs, 3 Draw: 4 flip throughs | Pass
3.2.37 |  |  |  | Options: Set Difficulty: Medium | Flip throughs set, dependent on draws: 1 Draw: 2 flip throughs, 3 Draw: 3 flip throughs | Pass
3.2.38 |  |  |  | Options: Set Difficulty: Hard | Flip throughs set, dependent on draws: 1 Draw: 1 flip throughs, 3 Draw: 1 flip through | Pass
3.2.39 |  |  |  | Options: Extra Settings: Select Timer check box | Turns on game timer | Pass
3.2.40 |  |  |  | Options: Extra Settings: Select Win Animation check box | Turns on end game win animation | Pass
3.2.41 |  |  |  | Options: Extra Settings: Select Win Sounds check box | Turns on end game sfx | Pass
3.2.42 |  |  |  | Options: Extra Settings: Deselect Timer check box | Turns off game timer | Pass
3.2.43 |  |  |  | Options: Extra Settings: Deselect Win Animation check box | Turns off end game win animation | Pass
3.2.44 |  |  |  | Options: Extra Settings: Deselect Win Sounds check box | Turns off end game sfx | Pass
3.2.45 |  |  |  | Options: Click Accept Options button | All options settings are saved, Options dialogue is closed
3.3 | GUI Interaction
3.3.1 | Kailab | UI | Manual | Undo Stack move using Ctrl-Z | Stack Moves back to Last Position. | Fail, Stack does not Move. | Serious
|  |  |  | Move Cards to Valid Positions | Cards move to Designated Position. | Fail | Serious |  | Kailab
3.3.2 |  |  |  | Move Cards to Valid Positions(Added Fix) | Cards move to Designated Position. | Fail for only moving to Collumns | Serious |  | Kailab
3.3.3 |  |  |  | Move Cards to Valid Positions(Editted Fix) | Cards move to Designated Position. | Pass | OK
|  |  |  | Move Valid Stack to Collumn | Selected Stack moves to Position | Pass | OK
|  |  |  | Double Click Auto Move Card | Card goes to Ace Pile, Collumn, or Open Slot | Pass | OK
|  |  |  | Right Click Discard Pile | Shows Card below Current Card | Pass | OK
|  |  |  | Click Empty Deal Pile to Reset | Place all Discard Pile back into Deal Pile | Pass | OK
|  |  |  | Click Deal Pile to Flip Card into Discard Pile | Top of Deal Pile goes to Discard Pile | Pass | OK
|  |  |  | Click Card to Highlight | Card's Color Changes | Pass | OK
|  |  |  | Click Card again to UnHighlight | Card's Color Reverts to Original | Pass | OK
|  |  |  | Click anywhere to Cancel Card Selection | Card's Color Reverts to Original and does not get Sent Anywhere when Clicking another Card | Pass | OK
|  |  |  | Win Game | Fireworks Display | Fail, Delayed until after Play Again | Minor
|  |  |  | Click Fireworks to Start New Game | New Game is Created | Fail until Fireworks Stop Playing | Minor
|  |  |  | Exit and Save Game | Game is Saved to Continue Playing | Pass
4 | Enhancements
4.1 | Graphics / Sounds
| Jesse |  |  | 1) Restart Game menu item instead of Ctrl+Z all the way to beginning 2) Sound effects for card clicks, moves, and ace pile completion, 3) Background from user files 4) Cancel button on close window dialog 5) Warning about Check Update opening browser 6) Cancel button on Check Update dialog 7) Background from user file 8) Ability to clear stats by individual difficulty/draw combo 9) Deck through dialogue changed to Play Again / Restart / Exit buttons 10) Confirmation dialogue before New Game
| Kailab |  |  | 11)Add a container or something to the cards so they can be tested with Jubula(Optional).
| Lizz |  |  | 12) Make deck background change immediately instead of starting new game like background does
4.2 | Gameplay
1) Difficulty Modes-
a)Easy- cards don't have not alternate color and flip one card at a time from draw pile
b)Normal- as it is
c)Hard- timer , flip three at a time
2) Option to change to tradition game with seven rows (only if there's time and we're ambitious)
3) Game modes(Check other book marks)
| Kailab |  |  | 4) Auto finish once all the cards are visible and all that is required is to place all the cards into the ace piles(Time permitted)
| Jesse |  |  | 5) Reverse mode: Empty spots filled with Aces, cards ascend in alternating suits; Object is to build in descending order on King Piles
4.3 | System
4.3.1 | Josh | General | Manual | UI/Gameplayer Integration | Non-integrated Components. | UI is currently integrated with the game processing. | Moderate | Ex: Card extends JComponent, should be seperate Card class from "CardImage" class that contains the card.
4.3.2 |  | General | Manual | Datatypes | Enum, Sets, constants, etc. | Values stored as strings and integers. No final constants used for strings. | Moderate
4.3.3 |  | General | Manual | Documentation | JavaDocs set up for all Classes and public funcions. | Javadocs only set up for classes. No code comments. | Minor
4.4.4 |  | Card.java, related classes. | Manual | Card creation | Simple method to create cards. | card requires 4 variables: String suit, int number, int deckNumber, int fullNumber | Moderate | Added complexity allows for invalid cards to be created.
Note on D1: jUnit TestNG Jubula Manual (etc)
Note on H1: OK: Works as-is. Minor: Won't effect opperations. Moderate: May provide minor difficulty, game still completable. Serious: Makes game unplayable or near-unplayable. Critical: Breaks computer operations (crash, file del, etc).

## Original Test Plan
Note: Some tests may work under multiple types depending on the action(s) required.
Unit Testing
Class | Action
AcePile | push() Success if the next card is the correct suit.
isValidMove() true if push() would be accepted.
Card | isHighlighted() should produce correct response after highlight() and unHightlight() commands. isFaceUp() should produce correct response after setFaceUp() and setFaceDown() commands. isValidSuit() should return true for all valid cards. getNumber(), getSuit(), getColor(), and getFullNumber() should all return correct values for each card.
Column | push() should only allow a next card of the opposite color, or King on a empty column. isValidMove() should only show true if push() would be accepted.
DiscardPile | push(), peek(), and pop() should all properly interact with the calling stack.
SingleCell | push() and isValidMove() should only be valid when the cell is empty.
Integration Testing
Class | Action/Expected Result
CardStack | Vector<Card> cardspush(), peek(), and pop() should all properly interact with the local Vector<Card> and any related stacks.
DealDeck | DiscardPile discardPilepush() should not be allowed (all changes through swapping cards with discardPile). setDifficulty() and setDrawCount() should both work. hasDealsLeft() should be false only when the player is out of deals.
Deck | LinkedList<Card> deckcreateCard() should create the correct suit, card number, deck number, and full card number. shuffle() should properly randomize the deck.
SolitaireBoard | Column[4] columns DiscardPile discardPile DealDeck dealDeck AcePile[4] acePiles SingleCell[4] cellsAll fields should have the correct values on start. All further interactions tested within System and UI Testing.
System and UI Testing
Action | Expected Result
Discard Pile Flip | Deck should cycle Deck-Through-Limit times, flipping Deck-Through-Limit minus one times.
Deck Through Limit | Draw 1 Card Draw 3 Cards Throughs Easy - 3 Med. - 2 Hard - 1 Easy - 4 Med. - 3 Hard - 2
Moving Card to New Location | Card to be moved should highlight when clicked. Alternating color cards should move to selected pile. Highlight on same colored cards should deactivate when attempting to move to invalid pile.
Moving Stack to New Location | Substack should highlight when top card of substack is clicked. Substack follows valid card move restrictions based on top card.
Adding Card to Ace Pile | Ascending sequential cards of same suit are added to Ace Piles Highlight on all other cards deactivates when attempting to move to invalid pile. Cards should move automatically to the appropriate Ace pile when double clicked.
Adding Card to Empty Pile | Kings should move to empty piles, highlight on all other cards should deactivate when attempting to move to invalid pile.
Winning the game | Fireworks and music should play based on settings. Fireworks pop up should immediately display on top level of GUI.
Starting a game | User should be able to start a new game by selecting the Game/New Game JMenu item or by pressing F2 key.
Undoing last move | User should be able to undo previous move, all the way back to the beginning of the game by selecting the Game/Undo Last Move JMenu item or by pressing Ctrl + Z.
Receiving Hints | User should be able to generate a Hint dialogue by selecting the Hint JMenu item or by pressing the &lsquo;h&rsquo; key and close dialogue by clicking the Ok JButton or the window&rsquo;s close button.
Accessing Stats | User should be able to generate a Stats dialogue by selecting the Stats JMenu item or by pressing the F4 key. User should be able to close the dialogue using the Close JButton or the window&rsquo;s close button. User should be able to clear the stats by clicking the Clear JButton; clicking the Clear button should close the dialogue.
Changing Options | User should be able to generate Options dialogue by selecting the Options JMenu item or by pressing the F5 key. User should be able to select any combination of the following options and confirm by clicking the Accept JButton: Card Draw: Draw One Draw Three Difficulty: Easy Medium Hard Extra Settings (On/Off): Timer Win Animations Win Sounds Clicking the Accept button should also close the dialogue. User should be able to close dialogue without changing options by clicking the Close JButton or the window&rsquo;s close button. Options should update after starting new game.
Changing Appearance. | User should be able to generate a Change Appearance dialogue by selecting the Change Appearance JMenu item or by pressing the F7 key. User should be able to select any deck/background combination and confirm by clicking the Choose This Set-Up JButton. Clicking button should also close the dialogue. User should be able to close the dialogue without changing options by clicking the window&rsquo;s close button. Backgrounds should update immediately. Deck should update when starting new game.
Exiting Program | User should be able to exit the program by selecting the Exit JMenu item or the window&rsquo;s close button. User should be prompted to save game if current game isn&rsquo;t finished. The program should exit after selecting either Save dialogue option is chosen.
Accessing Help | User should be able to generate a Help dialogue explaining the rules of the game by selecting the Help/View Help JMenu item or by pressing the F1 key. User should be able to exit the Help dialogue by clicking the OK JButton or the window&rsquo;s close button.
Accessing Credits | User should be able to generate a dialogue containing game credits by selecting the Help/About Game JMenu item. User should be able to exit the About Game dialogue by clicking the OK JButton or the window&rsquo;s close button.
Software Updates | User should be able to check for updated versions by selecting the Help/Check for Updates JMenu item. Selecting the menu item should close the dialogue and open the Four Row Solitaire project page located athttps://sourceforge.net/projects/fourrow/
Enhancement Ideas
In Class | Current Functionality